## Sheet1
Example QSI Project Plan
Task | 2018-10-01 | 2018-11-01 | 2018-12-01 | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01 | 2019-05-01 | 2019-06-01 | 2019-07-01 | 2019-08-01 | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01
STAGE 1
Seek agreement from the Board of organisation to pursue QSI
Write Project Implementation Document (PID) | bar: 2018-10-01
Agree comtrolled document template and numbering system | bar: 2018-10-01 to 2018-11-01
Obtain approval for PID | bar: 2018-11-01
Send letter from Board to QSI team committing to Quality Improvement
STAGE 2
Form project team | bar: 2018-11-01 to 2018-12-01
Contact QSI Officer for support | bar: 2018-11-01 to 2018-12-01
Contact local accredited imaging services for advice/learning | bar: 2018-11-01 to 2018-12-01
Go over PID and start top level gap analysis | bar: 2018-12-01 to 2019-01-01
List gaps to processes and documentation | bar: 2019-01-01
Present project plan and gap analysis to project team members | bar: 2019-02-01
Task sub teams with process updates and documentation tasks | bar: 2019-02-01
Write QSI Quality Manual System requirements | bar: 2019-02-01 to 2020-02-01
Write QSI Quality Manual | bar: 2019-01-01
STAGE 3 | bar: 2019-01-01
Define Quality objectives and KPIs | bar: 2019-02-01
Decide on format of Management Review Committee | bar: 2019-03-01
Draw up internal audit plan | bar: 2019-04-01 to 2019-05-01
Train internal auditors | bar: 2019-05-01 to 2019-06-01
Conduct audits | bar: 2019-05-01 to 2020-04-01
Report on audits and documentation status to Management Review Committee | bar: 2019-05-01; 2019-07-01; 2019-09-01; 2019-11-01; 2020-01-01; 2020-03-01; 2020-05-01
Approve new documentation and post to QMS and/or intranet | bar: 2019-07-01 to 2020-03-01
STAGE 4 (OPTIONAL) | bar: 2019-05-01; 2019-07-01; 2019-09-01; 2019-11-01; 2020-01-01; 2020-03-01; 2020-05-01
Arrange and attend UKAS training workshop days | bar: 2018-11-01 to 2019-01-01
Transfer documentation to UKAS Traffic Light Ready system | bar: 2019-11-01
Make formal application for UKAS accreditation | bar: 2019-12-01
Document review by UKAS completed | bar: 2020-01-01
Correct any findings raised by UKAS at document review stage | bar: 2020-02-01
Arrange and complete site visit by UKAS inspectors | bar: 2020-03-01
Correct any findings raised at site inspection | bar: 2020-04-01 to 2020-05-01
Obtain accreditation | bar: 2020-06-01
STAGE 5 (OPTIONAL) | bar: 2020-06-01
Ongoing self -accreditation | bar: 2020-07-01
Four yearly re-accreditation
Set up Quality Management System (QMS)
Submit final spec for any business case needed | bar: 2018-11-01 to 2018-12-01
Obtain quotations needed | bar: 2018-12-01
Secure support and funding from senior management | bar: 2019-01-01 to 2019-02-01
QMS installation | bar: 2019-03-01 to 2019-04-01
QMS operator training | bar: 2019-05-01 to 2019-07-01